## Core Team Role Definitions
Business/Executive Sponsor | Implementation Lead | Subject Matter Experts (1-3) | Tool Administrator
•Define strategic goals of pilot and sets business objectives. | •Coordinates day-to-day. | •System Engineer / Requirements Mgmt / Test Management SMEs who are empowered representative of the teams that could potentially use Jama. | •Responsible for learning administration of Jama.
•Chooses team / product for initial Jama implementation. | •Main point of contact to Jama CSM | •Provides direct feedback on scope of Jama usage scenarios and optimization. | •If self-hosted, Sys Admin also needed to coordinate any on-premises installation/upgrade activities.
•Should understand your internal processes and which resources should be involved.

## Core Team Roster
Core Team | Name | Email | Team/Role
Jama CSM
Business/Executive Sponsor
Implementation Lead
System Administrator (Self-Hosted Only)
Organization Administrator
Functional Area SME 2
Functional Area SME 3
Functional Area SME 4
Functional Area SME 5

## Jama Project Plan-External
Phase | Tasks/Milestones | Core Team Role | Suggested Timeline
Ready | Confirm receipt of your license confirmation email and test that you are able to log on using the provided credentials | Business/Executive Sponsor | Week 1
| Form your Onboarding Core Team | Implementation Lead | Week 1
| Identify and register Named Support Contacts | Implementation Lead | Week 1
| Register for the Jama Software Community Site | Core Team | Week 1
| Bookmark the Onboarding Jama Connect resource page on the Community Site for easy access | Core Team | Week 1
| Capture the "Why": Define business goals, objectives & KPIs | Core Team | Week 1
| Gather process-related materials (e.g., project SOPs and workflows, sample artifacts/templates) | Core Team | Week 1
| Distribute and Share Getting Started Videos | Implementation Lead | Week 1
| Provision and prepare environments (If Self-Hosted) | System Administrator (Self-Hosted Only) | Week 1
| Register for Organization Adminstrator Training | Implementation Lead | Week 1
| Conduct internal alignment meetings (align team with project plan, roles & responsibilities, project objectives) | Core Team | Week 1
| Review the Jama Software Customer Success Catalogue to familiarize yourself with available professional services | Core Team
Set | Create user accounts for Core Team members | Implementation Lead | Week 2
| Register Core Team for Organization Admin Training | Core Team | Week 2
| Register key stakeholders unfamiliar with Jama Connect for Jama 101 Training | Core Team | Week 2
| Complete gathering current state (as-is) artifacts/processes | Core Team | Week 2
| Document Current State (As-Is) processes | Core Team | Week 2
| Document and determine desired state (to-be) processes (high-level) | Core Team | Week 2
| Document Gap Analysis between desired state processes and standard Jama data set | Core Team | Week 2
| OPTIONAL: Request remote Data Model and Configuration Session(s) with Jama Consultant (Success Program Offering) | Implementation Lead | Week 2
| OPTIONAL: Request guidance to create a Strategic Deployment Plan | Implementation Lead | Week 2
| Use the Data Model Gap Analysis to update your Jama Connect configuration to match desired state | Organization Administrator | Week 3
| Create a Template Project | Organization Administrator | Week 3
| Identify and Document KPIs and other project metrics | Core Team | Week 3
| Create Advanced Filters to capture data needed to track KPIs and other project metrics | Organization Administrator | Week 3
| OPTIONAL: Request guidance to create a Strategic Deployment Plan | Implementation Lead | Week 3
| OPTIONAL: Request a Personalized Go-Live Consulting Session | Implementation Lead | Week 3
| OPTIONAL: Request Power User Training for your Core Team and other stakeholders | Implementation Lead | Week 3
| Identify and document project roles for Jama Connect users | Core Team | Week 4
| Create user groups and permission schemes in the Template Project | Organization Administrator | Week 4
| Develop a plan for end user training | Core Team | Week 4
| Identify initial projects for Jama Connect launch | Core Team | Week 4
| Create project spaces in Jama Connect for initial projects | Organization Administrator | Week 4
| Plan for importing existing project data into Jama Connect | Core Team | Week 4
| OPTIONAL: Request an Optimization Session for your User Group and Permissions scheme | Implementation Lead | Week 4
| OPTIONAL: Request Personalized User Training for assistance with your end user training plan | Implementation Lead | Week 4
| OPTIONAL: Request training and guidance on importing documents to Jama Connect | Implementation Lead | Week 4
| Determine what project milestones and checkpoints Jama Connect needs to support for approving requirements | Core Team | Week 5
| Establish item type workflows to provide guardrails for the identified review checkpoints | Organization Administrator | Week 5
| Configure the stream settings to enable collaboration in Jama Connect | Organization Administrator | Week 5
| Configure Review Center templates to establish guardrails for how reviews are conducted in Jama Connect | Organization Administrator | Week 5
| Identify reporting and data export needs for projects and review the available report and export templates to identfy necessary changes or updates | Core Team | Week 5
| Review available Community Reports | Core Team | Week 5
| Add any Community Reports to your instance for testing | Organization Administrator | Week 5
| OPTIONAL: Request a Collboration and Review Workflow Consultation | Implementation Lead | Week 5
| OPTIONAL: Request Training for Custom Reports using Velocity | Implementation Lead | Week 5
| OPTIONAL: Request Training for Basic Document Export Templates using Microsoft Word | Implementation Lead | Week 5
| OPTIONAL: Request scopring for Custom Reports to be developed by Jama Software | Implementation Lead | Week 5
Go | Conduct Launch Readiness Assessment: | Core Team | Week 6
| All needed item types are configured with updated pick list values and fields to capture requirement metadata | Core Team | Week 6
| Relationship rules have been established to enable traceability | Core Team | Week 6
| User groups and permissions have been established | Core Team | Week 6
| Workflows, Review Center, and Streams have been configured to optimize collaboration | Core Team | Week 6
| Training plan for new users is ready | Core Team | Week 6
| Complete import of existing project data for initial Jama Connect Projects | Organization Administrator | Week 6
| Transition Core Team to a Jama Connect Governance Team and schedule recurring meetings to evaluate any configuration change requests | Implementation Lead | Week 6
| OPTIONAL: Request remote Data Model and Configuration Session(s) with Jama Consultant (Success Program Offering) | Implementation Lead | Week 6
| OPTIONAL: Request guidance to create a Strategic Deployment Plan | Implementation Lead | Week 6
| OPTIONAL: Request a Personalized Go-Live Consulting Session | Implementation Lead | Week 6
| Create accounts for initial Jama Connect users and add them to appropriate user groups | Organization Administrator | Week 7
| Share Training Resources with your project teams | Implementation Lead | Week 7
| Activate end user training plans | Implementation Lead | Week 7
| OPTIONAL: Request an Optimization Session to plan for how to collect and incorporate user feedback to your Jama Connect configuration | Implementation Lead | Week 7
| OPTIONAL: Request a Collboration and Review Workflow Consultation | Implementation Lead | Week 7
| Complete Integration Septup and Initial Configuration (if applicable): | Organization Administrator | Week 8
| Determine End to End Integration processes | Core Team | Week 8
| Determine items/attributes to be mapped | Core Team | Week 8
| Environment/Server Ready for install (if on-premise installation) | System Administrator (Self-Hosted Only) | Week 8
| Perform Application install (if on-premise installation) | System Administrator (Self-Hosted Only) | Week 8
| Perform Item/Attribute Mapping | Organization Administrator | Week 8
| OPTIONAL: Request Integration Hub Setup for Live Traceability | Implementation Lead | Week 8
| Schedule kick off meetings with project teams | Implementation Lead | Week 8
Check | Collect and Incorporate Stakeholder Feedback into Jama Configuration, Processes and Procedures | Core Team | Week 9 and ongoing
| Assess impact of changes to team against current process | Core Team | Week 9 and ongoing
| End-User Support approach established | Core Team | Week 9 and ongoing
| OPTIONAL: Request a Trace Debt Diagnostic | Implementation Lead | Week 9 and ongoing
| OPTIONAL: Request a Trace Score Assessment | Implementation Lead | Week 9 and ongoing
| OPTIONAL: Request a Trace Debt Diagnostic | Implementation Lead | Week 9 and ongoing
| OPTIONAL: Request a Requirement Quality Assessment | Implementation Lead | Week 9 and ongoing
| OPTIONAL: Request a Requirements Authoring Workshop | Implementation Lead | Week 9 and ongoing
| OPTIONAL: Request a Variant Management and Reuse Consultation | Implementation Lead | Week 9 and ongoing
| OPTIONAL: Request a Release Management Consultation | Implementation Lead | Week 9 and ongoing
| OPTIONAL: Request a Change Management Consultation | Implementation Lead | Week 9 and ongoing
| OPTIONAL: Request a Test Management Consultation | Implementation Lead | Week 9 and ongoing
| OPTIONAL: Request a Risk Management Consultation | Implementation Lead | Week 9 and ongoing
| OPTIONAL: Request REST API Training | Implementation Lead | Week 9 and ongoing
Ongoing Support | Schedule an ongoing success planning meeting with your Jama Software Customer Success Manager | Implementation Lead | Week 12
| As needed, request consulting, technical, or benchmarking services from the Customer Success Catalouge | Implementation Lead | Ongoing

## Named Support Contacts
Name | Email
Named Support Contacts Explained​
Register/Change Named Support Contacts