## Team
Roles | Business/Executive Sponsor | Implementation Lead | Organization Administrator | Subject Matter Experts (SMEs)
Responsabilities | • Defines strategic goals of pilot and sets business objectives. • Chooses team / product for initial Jama implementation. | • Coordinates day-to-day • Main point of contact to Jama CSM • Understands internal processes and which resources should be involved | • Responsible for administration of Jama | • SysEng/ReqsMgmt/TestMgmt SMEs who are empowered representative of the teams that will use Jama • Provide input and feedback on Jama usage scenarios and optimization
Core Team Roster
| Role | Name | Email | Team/Role
Jama CSM
Business/Executive Sponsor
Implementation Lead
Organization Administrator
Functional Area SME 2
Functional Area SME 3
Functional Area SME 4
Functional Area SME 5
Named Support Contacts
| Name | Email
Named Support Contacts Explained​
Register/Change Named Support Contacts

## Roadmap
KPIs
Rank | Goal | Metric | Target Date | Status | Notes
1
2
3
4
Jama Connect Implementation Plan
Phase | Business/Product Area | Scope | Go-Live Date | Status | Notes
1
2
3
4
Success Credit Utilization Plan | [5 empty] | Customer Success Catalog
Credit | Offering | Outcome | Start Date | Status | Notes
1
2
3
4
5
6
7
8
9
10
11
12

## Onboarding Plan
Phase | Tasks/Milestones | Success Credit? | Core Team Role | Target Completion Date | Status | Column1
Ready | Confirm receipt of your license confirmation email and test that you are able to log on using the provided credentials |  | Business/Executive Sponsor
| Form your Onboarding Core Team |  | Implementation Lead
| Identify and register Named Support Contacts |  | Implementation Lead
| Register for the Jama Software Community Site |  | Core Team
| Bookmark the Onboarding Jama Connect resource page on the Community Site for easy access |  | Core Team
| Capture the "Why": Define business goals, objectives & KPIs |  | Core Team
| Gather process-related materials (e.g., project SOPs and workflows, sample artifacts/templates) |  | Core Team
| Distribute and Share Getting Started Videos |  | Implementation Lead
| Register for Organization Adminstrator Training |  | Implementation Lead
| Conduct internal alignment meetings (align team with project plan, roles & responsibilities, project objectives) |  | Core Team
| Review the Jama Software Customer Success Catalogue to familiarize yourself with available professional services |  | Core Team
Set | Create user accounts for Core Team members |  | Implementation Lead
| Register Core Team for Organization Admin Training |  | Core Team
| Register key stakeholders unfamiliar with Jama Connect for Jama 101 Training |  | Core Team
| Document Current State processes + artifacts |  | Core Team
| Document and determine Desired State processes + artifacts |  | Core Team
| Document Gap Analysis between desired state processes and standard Jama data set |  | Core Team
| OPTIONAL: Request remote Data Model and Configuration Session(s) with Jama Consultant | Yes | Implementation Lead
| OPTIONAL: Request guidance to create a Strategic Deployment Plan | Yes | Implementation Lead
| Create a Template Project |  | Organization Administrator
| Identify and Document KPIs and other project metrics |  | Core Team
| Create Advanced Filters to capture data needed to track KPIs and other project metrics |  | Organization Administrator
| OPTIONAL: Request guidance to create a Strategic Deployment Plan | Yes | Implementation Lead
| OPTIONAL: Request a Personalized Go-Live Consulting Session | Yes | Implementation Lead
| OPTIONAL: Request Power User Training for your Core Team and other stakeholders | Yes | Implementation Lead
| Identify and document project roles for Jama Connect users |  | Core Team
| Create user groups and permission schemes in the Template Project |  | Organization Administrator
| Develop a plan for end user training |  | Core Team
| Identify initial projects for Jama Connect launch |  | Core Team
| Create project spaces in Jama Connect for initial projects |  | Organization Administrator
| Plan for importing existing project data into Jama Connect |  | Core Team
| OPTIONAL: Request an Optimization Session for your User Group and Permissions scheme | Yes | Implementation Lead
| OPTIONAL: Request Personalized User Training for assistance with your end user training plan | Yes | Implementation Lead
| OPTIONAL: Request training and guidance on importing documents to Jama Connect | Yes | Implementation Lead
| Determine what project milestones and checkpoints Jama Connect needs to support for approving requirements |  | Core Team
| Establish item type workflows to provide guardrails for the identified review checkpoints |  | Organization Administrator
| Configure the stream settings to enable collaboration in Jama Connect |  | Organization Administrator
| Configure Review Center templates to establish guardrails for how reviews are conducted in Jama Connect |  | Organization Administrator
| Identify reporting and data export needs for projects and review the available report and export templates to identfy necessary changes or updates |  | Core Team
| Review available Community Reports |  | Core Team
| Add any Community Reports to your instance for testing |  | Organization Administrator
| OPTIONAL: Request a Collboration and Review Workflow Consultation | Yes | Implementation Lead
| OPTIONAL: Request Training for Custom Reports using Velocity | Yes | Implementation Lead
| OPTIONAL: Request Training for Basic Document Export Templates using Microsoft Word | Yes | Implementation Lead
| OPTIONAL: Request scopring for Custom Reports to be developed by Jama Software | Yes | Implementation Lead
Go | Conduct Launch Readiness Assessment: |  | Core Team
| All needed item types are configured with updated pick list values and fields to capture requirement metadata |  | Core Team
| Relationship rules have been established to enable traceability |  | Core Team
| User groups and permissions have been established |  | Core Team
| Workflows, Review Center, and Streams have been configured to optimize collaboration |  | Core Team
| Training plan for new users is ready |  | Core Team
| Complete import of existing project data for initial Jama Connect Projects |  | Organization Administrator
| Transition Core Team to a Jama Connect Governance Team and schedule recurring meetings to evaluate any configuration change requests |  | Implementation Lead
| OPTIONAL: Request remote Data Model and Configuration Session(s) with Jama Consultant | Yes | Implementation Lead
| OPTIONAL: Request guidance to create a Strategic Deployment Plan | Yes | Implementation Lead
| OPTIONAL: Request a Personalized Go-Live Consulting Session | Yes | Implementation Lead
| Create accounts for initial Jama Connect users and add them to appropriate user groups |  | Organization Administrator
| Share Training Resources with your project teams |  | Implementation Lead
| OPTIONAL: Request an Optimization Session to plan for how to collect and incorporate user feedback to your Jama Connect configuration | Yes | Implementation Lead
| OPTIONAL: Request a Collboration and Review Workflow Consultation | Yes | Implementation Lead
| Complete Integration Septup and Initial Configuration (if applicable): |  | Organization Administrator
| Determine End to End Integration processes |  | Core Team
| Determine items/attributes to be mapped |  | Core Team
| Perform Item/Attribute Mapping |  | Organization Administrator
| OPTIONAL: Request Integration Hub Setup for Live Traceability | Yes | Implementation Lead
| Schedule kick-off meetings with project teams |  | Implementation Lead
Check | Collect and Incorporate Stakeholder Feedback into Jama Configuration, Processes and Procedures |  | Core Team
| Assess impact of changes to team against current process |  | Core Team
| Establish End-User Support approach |  | Core Team
| OPTIONAL: Request a Trace Debt Diagnostic | Yes | Implementation Lead
| OPTIONAL: Request a Trace Score Assessment | Yes | Implementation Lead
| OPTIONAL: Request a Trace Debt Diagnostic | Yes | Implementation Lead
| OPTIONAL: Request a Requirement Quality Assessment | Yes | Implementation Lead
| OPTIONAL: Request a Requirements Authoring Workshop | Yes | Implementation Lead
| OPTIONAL: Request a Variant Management and Reuse Consultation | Yes | Implementation Lead
| OPTIONAL: Request a Release Management Consultation | Yes | Implementation Lead
| OPTIONAL: Request a Change Management Consultation | Yes | Implementation Lead
| OPTIONAL: Request a Test Management Consultation | Yes | Implementation Lead
| OPTIONAL: Request a Risk Management Consultation | Yes | Implementation Lead
| OPTIONAL: Request REST API Training | Yes | Implementation Lead
Ongoing Support | Schedule an ongoing success planning meeting with your Jama Software Customer Success Manager |  | Implementation Lead
| As needed, request consulting, technical, or benchmarking services from the Customer Success Catalouge |  | Implementation Lead

## Project Go-Live Checklist
| Topic | Configuration Item | Tips | Status | Notes
Core Topics | Item Type Definition | Identify Item Types to be configured
|  | Configure Item Types | Note: can launch with minimum-viable framework and add in VnV, Arch/ICD, Risk, etc. later
|  | - Configure Fields for each Item Type | Best practice: every field configured should have a clear purpose
- Define Pick List values for single/multi select Fields
|  | - Update Field settings - Sync, Suspect, Required, etc. | Best practice: complete this towards the end of configuration
- Create Editor Templates
| TIM | Define Traceability Information Model(s)
|  | Define Relationship Type(s) to be used | Best practice: start with "Related to" and incorporate additional types as needed
|  | Apply Relationship Ruleset to projects | Note: copying a project also copies its TIM schema
| Project Templates | Create Project Template(s)
- Item Type Selection
- Relationship Ruleset
- Permissions
- Filters
- Define Project Structure
| User Groups and Permissions | Create Organization User Group(s) | Note: define in the Organization tab
|  | Create Project User Group(s) | Note: define in the Project tab
|  | Configure Organization Permissions | Best practice: manage permissions by user group
|  | Configure Project Permissions | Best practice: manage permissions by user group
Advanced Topics | Workflows | Configure Workflows for all applicable Item Types
- Set Transitions, Notifications, Locks, Permissions
|  | - Allow Projects to Override (if applicable) | Best practice: avoid the need for project-specific overrides where possible
| Collaboration and Review | Configure Review Center settings | Note: Peer and Approval reviews may be configured independantly
Configure Review Center settings
|  | Add Reporting Templates for exporting needs | Note: additional templates may be found on the Community Reports GitHub
| Additional Functions | Create public Filters for ease of use
Establish Reuse and Sync use case + process (if applicable)
Define Test Management process (if applicable)
| Admin. | Delete unused Jama sample data and configuration items
Create end user training/resource projects
| Integrations | JCI
- Jira: ID backlog items to include in traceability
- Jira: ID fields/metadata to sync between JC and Jira
- Jama: Create item types correespondgin to synced Jira items
- Jama: create needed item types, add to projects
- Jama: update TIM with new items
- Jama: add containers for new item types

## List of Open Points
No. | Prio | Title | Details | Status | Solution Complexity (est.) | Related Topics | Planned Date | Notes | Next Steps | Soution
1
2
3
4
5

## Resources
Topic | Resource | Notes
Tool Enablement | Jama Connect 101 Tutorials | Video tutorials for key Jama Connect features and functions. Available on demand, may require community login.
| Jama Connect Admin Tutorials | Video tutorials for admin responsibilities in Jama Connect. Available on demand, may require community login.
| Jama Connect User Guide | Jama Connect user manual
Process Enablement | The Essential Guide to Requirements Management and Traceability
Jama Connect Onboarding Guide
How to Create a Template Project
Support | Jama Software Support | Submit support tickets. Requires NSC designation (see Team) and support account.
| Jama Software Knowledge Base | Search articles for answers to technical questions, process best practices, and everything in between. Requires support account.
| Jama Software Community Site | Engage with other Jama Connect users, access industry resources, and stay up to date with upcoming events. Requires community account.
Other Resources | Community Reports | Jama Software's Github page for advanced report templates. Free to download and use on your Jama Connect instance.
| API Dev Site | Developer resources for the Jama Connect REST API
| Register/Change Named Support Contacts | Self-serve management of NSCs
| Jama Labs | Info on Jama Software's AI initiatives

## Validation
Prio |  | Status | Solution Complexity
5 | low | To Do | low | ≤ 1hr
3 | mid | Scheduled | mid | 1-2 hrs
1 | high | In Progress | high | 2-4 hrs
On Hold
Complete